## Sheet1
Team # Project Plan
TASK FOCUS | TASK LETTER | TASK DESCRIPTION | DATE START | DATE END | PREDECESSOR TASK(s) | RESOURCE(s)
Database
| A | Create Database | 2025-06-29 | 2025-07-06 |  | Cole
| B | Create Stored Procedures | 2025-07-07 | 2025-07-10 | A | Cole
| C | Populate Look Up Tables | 2025-07-11 | 2025-07-13 | B | Cole
Software Development
| D | Create Python GUI | 2025-06-29 | 2025-07-20 |  | Jason
| E | Create HTML Page | 2025-06-29 | 2025-07-10 |  | Adam
| F | Create Report & KDS Pages | 2025-07-14 | 2025-07-21 | C, E | Adam & Cole
Unit Test
| G | Test Python GUI | 2025-07-21 | 2025-08-01 | D | Team
| H | Test HTML | 2025-07-11 | 2025-07-17 | E | Adam & Cole
| I | Assist with HTML & Python | 2025-07-14 | 2025-08-01 |  | Cole
| J | Test Report Pages | 2025-07-22 | 2025-08-01 | F | Adam & Jason
| K | Test on Raspberry Pi | 2025-07-21 | 2025-08-01 | G | Jason & Cole
Integration Test
| L | Develop Testing Plan | 2025-07-21 | 2025-07-23 |  | Jason
| M | Test Whole Application | 2025-08-02 | 2025-08-12 | L, D, E, F, G | Team
User Test
| N | Develop Test Plan | 2025-08-02 | 2025-08-05 | L | Jason
| O | Conduct User Test with users | 2025-08-03 | 2025-08-06 | M,N | Team
Presentation Development
| P | Develop Presentation | 2025-08-07 | 2025-08-09 |  | Jason
| Q | Practice Presentation | 2025-08-10 | 2025-08-12 | P | Team
Present Project
| R | Present Project | 2025-08-13 | 2025-08-13 | Q | Team