## Sheet1
| Team # Project Plan | This color indicates changes to doc
TASK FOCUS | TASK LETTER | TASK DESCRIPTION | DATE START | DATE END | PREDECESSOR TASK(s) | RESOURCE(s)
Database
| A | Create Database | 2025-06-29 | 2025-07-06 |  | Cole
| B | Create Stored Procedures | 2025-07-07 | 2025-07-14 | A | Cole
| C | Populate Look Up Tables | 2025-07-14 | 2025-07-20 | B | Cole
Software Development
| D | Create Python GUI | 2025-06-29 | 2025-07-20 |  | Jason & Adam
| E | Create HTML Page | 2025-06-29 | x |  | Adam
| F | Create Update Page | 2021-03-01 | 2021-03-20 |  | Ty Urup
| G | Create Report Pages | 2021-03-13 | 2021-03-20 | C, D, E | Adam
| H | Create Whatever you are creating | 2021-03-21 | 2021-04-02 | F | Ty Urup
Unit Test
| I | Test Python GUI | 2025-07-21 | 2021-03-20 | D | Team
| J | Test HTML | x +1day | 2021-03-15 | E | Adam & Cole
| K | Test Update Page | 2021-03-21 | 2021-03-18 | F | Team
| L | Test Report Pages | 2021-03-21 | 2021-03-30 | G | Team
| M | Test on Raspberry Pi | 2021-04-03 | 2021-04-10 | H | Jason & Cole
Integration Test
| N | Develop Testing Plan | 2021-04-01 | 2021-04-10 | C | Jason
| O | Test Whole Application | 2021-04-11 | 2021-04-18 | N, D, E, F, G, H | Team
User Test
| P | Develop Test Plan | 2021-04-11 | 2021-04-15 | N | Mark Spits
| Q | Conduct User Test with users | 2021-04-16 | 2021-04-22 | P, O | Team and Users
Presentation Development
| R | Develop Presentation | 2025-08-07 | 2025-08-09 |  | Jason
| S | Practice Presentation | 2025-08-10 | 2025-08-12 | R | Team
Present Project
|  | Present Project | 2025-08-13 | 2025-08-13 | S | Team